## Pipeline 2026-09-30
# | Video/title | Channel | Format | Status | Script (path · status) | Deadline / post date (AZ) | Shot list | Directions | Assets / kit location | Owner / next action
1 | An AI Got Into Government Files. Nobody Told It To. | PARADOCS10X | Short | FINAL, QA passed 3:23 PM Tue 9/29 after the re-voice (48.7 s). Ready to post. | scripts/batch-1-drafts.proofed.md (A1) · proofed. TTS as voiced: shorts/revoice/hack.tts.txt. (A1 header still says 'needs re-record + new edit'. That's stale; it's done.) | Post TODAY, Tue 9/29 (evening AZ) | 1) Official OpenAI logo slams in over a dark UI grid; 'ACCESS DENIED ×3' stack flips to a NON-PUBLIC folder 2) 'JUNE 18, 2026' stamp; cursor hits BLOCKED ×3 (labeled ILLUSTRATION); Wayback screenshot of the Medicare Statistics portal, push-in; Australia map pin 3) Two quote cards: PM ('didn't accept no for an answer') and OpenAI ('took actions we did not intend'); Ars Technica/BBC headline slices 4) Calendar counter Jun 18 → Sep 10 lands on 84 DAYS; envelope drops into a PUBLIC INBOX tile 5) The Record code snippet (/SASStoredProcess/guest) with a highlighter sweep; Guardian/AP 'halts training' headline; DOZENS counter 6) Neural-net glyph vs OpenAI logo split → end card DROP A COMMENT: WHO'S TO BLAME? | LOCKED FINAL, post as is (built and QA'd to this standard: kinetic word-pop captions, SFX, CTA end card held ≥0.6 s). Only open it in CapCut to fix something that QA flagged. Post the .revoice.mp4 only. Pin the comment and the sources from the publish copy. | Final: /workspace/shorts/tech-2026-09-29-ai-government-files.revoice.mp4 · Copy: shorts/publish-copy-2026-09-29-extra.md §A · QA: shorts/revoice/work_hack/qa/ | You: upload tonight, switch on YouTube Studio's AI-use setting, pin the comment. DON'T post tech-2026-09-29-ai-government-files.mp4, which is the retired-voice file.
2 | An AI Picked Stocks Since 2017. The S&P Won. (AIEQ vs S&P 500, Double-Checked) | The Meticulous Investor | Short | FINAL, QA passed 3:32 PM Tue 9/29 after the re-voice (27.4 s). Ready to post. | scripts/money-short-aieq-vs-spy.proofed.md · proofed. TTS: shorts/revoice/aieq.tts.txt | Wed 9/30 | 1) Payoff at frame 0: two growth lines diverging, logo labels AIEQ $22,600 vs SPY $34,400 2) AIEQ line redraws from '$10,000 · Oct 18, 2017' (AI-PICKED STOCKS) 3) DOUBLE-CHECKED stamp slams in; SPY ticker card slides in 4) SPY line races ahead to $34,400 5) Gap bracket −$11,800 (DID NOTHING. WON.) 6) 'THE REAL TEST: THE BENCHMARK' → end card WHICH AI FUND NEXT? / DROP A COMMENT | LOCKED FINAL, post as is (built and QA'd to this standard: kinetic word-pop captions, SFX, CTA end card held ≥0.6 s). Only open it in CapCut to fix something that QA flagged. Keep the persistent source/fees footer on screen. | Final: /workspace/shorts/invest-2026-09-29-aieq-vs-spy.revoice.mp4 · Copy: shorts/publish-copy-2026-09-29.md §2 · QA: shorts/revoice/work_aieq/qa/ | You: upload Wed, turn on the AI-use setting, pin 'Drop a comment: would you let a bot pick your stocks?'. Don't post invest-2026-09-29-aieq-vs-spy.mp4, which is the retired-voice file.
3 | Tesla's Roadster Just Got Its 13th Date | PARADOCS10X | Short | FINAL, QA passed 3:47 PM Tue 9/29 after the re-voice (34.75 s). Ready to post. | scripts/tech-short-roadster-16th-date.proofed.md · proofed (the file name says '16th', but the content is the 13th date). TTS: shorts/revoice/roadster.tts.txt | Wed 9/30 or Thu 10/1 AM. Must go out by Sun 10/4, or the VO's 'just moved' reads as dated. NEVER on or after Oct 15. | 1) Frame 0: giant '13' flipping calendar pages + '0 DELIVERED' stamp 2) Real @Tesla Sep 28 post, push-in + highlighter on 'New date is October 15'; OCT 1 struck → OCT 15 3) 4-day McGregor TX forecast strip (82% / 81% / 53% / dry) → '+14 DAYS' ruler 4) Official 2017 unveil clip (2–3 s, FOOTAGE: TESLA) + stamp 'NOV 2017 · PRODUCTION: 2020' 5) Years 2021 → 2025 stamp in and strike through → '2027–28?' 6) Day counter to 3,255 DAYS, 13 date cards stack, '13' slams in → end card FOLLOW FOR RECEIPTS / OCT 15? | LOCKED FINAL, post as is (built and QA'd to this standard: kinetic word-pop captions, SFX, CTA end card held ≥0.6 s). Only open it in CapCut to fix something that QA flagged. QA flagged 7 safe-zone hits, all graphics (storm-arrow tip and the tick bar), no text. Acceptable. | Final: /workspace/shorts/tech-2026-09-29-roadster-16th.revoice.mp4 · Copy: shorts/publish-copy-2026-09-29.md §1 · Research: research/roadster-receipts-prefill.md | You: upload Wed/Thu AM, turn on the AI-use setting, pin the 13-date comment. Don't post tech-2026-09-29-roadster-16th.mp4, which is the retired-voice file.
4 | 10-Year Treasury at 5.26%: Highest Since 2007 (The Rate) | The Meticulous Investor | Short | SKIPPED. Owner call Wed 9/30: do not post. (Was FINAL, QA passed 3:39 PM Tue 9/29.) | scripts/money-short-the-rate-10-year-5-24.proofed.md · proofed (the file name says 5-24, the content says 5.26%). TTS: shorts/revoice/rate.tts.txt | None. Skipped. | 1) Payoff at frame 0: 10-year yield line spikes to a glowing 5.26%, level with a 2007 marker 2) Zoom out 2007–2026: two dots at the same height, Jun 12, 2007 and Sep 29, 2026 3) Line snaps back to 'Aug 28 · 4.73%', then races up (+0.53) 4) A 7.03% rate tag drops onto a house outline (Freddie PMMS, week of Sep 24) 5) Payment cards $2,393 (5.98%) vs $2,669 (7.03%) → '+$276/mo' bracket 6) Pull back to the glowing 5.26% → end card FOLLOW FOR THE RATE | LOCKED FINAL, post as is (built and QA'd to this standard: kinetic word-pop captions, SFX, CTA end card held ≥0.6 s). Only open it in CapCut to fix something that QA flagged. If the Wed 9/30 close is above 5.26%, the 'matching its June 2007 high' line changes (see the script's publish-day check). | Final: /workspace/shorts/invest-2026-09-29-the-rate-10-year.mp4 (re-voiced in place) · Cover: /workspace/style/covers/money-the-rate.png · Copy: shorts/publish-copy-2026-09-29-extra.md §B · QA: shorts/build_rate/qa/ | None. Do not upload invest-2026-09-29-the-rate-10-year.mp4 or the SCRATCH file. The Treasury close check is no longer needed.
5 | Bot-trading explainer (flagship): Grok + Robinhood Agentic with a real $500 | The Meticulous Investor (per the script header) | Long (~36 min as drafted) | Script PROOFED v1 but BLOCKED: Ch7 placeholders wait on the Day-0 recording and the live $500 run. No VO and no edit yet. | scripts/money-long-ai-trading-flagship.proofed.md · proofed/blocked. Brief: scripts/briefs/ai-trading-flagship-brief.md | Research due Thu 10/1. Post date TBD, 'after Optimus' (the tracker proposes Thu Nov 26, conditional) | Cold open) Our own bar race of 6 AIs at $10K; 4 red bars; Robinhood fine-print quote card + NO PAPER MODE / NO CAPS stamps Ch1) 5-rung ladder (auto-deposit → robo → rules engine → copy trading → AI agent); WHO'S LIABLE meter; EXECUTE vs DRAFT broker table Ch2) SPIVA row-slam 78.78 / 85.59 / 92.89%; AIEQ vs SPY lines; 97-of-100 red dot grid; Morningstar gap lines Ch3) Robo flow + neutral fee table; 3 SEC case folders ($187M, $9M, 31%); BrokerCheck search mock Ch4) Four coin piles: 0.03% $656,720 → 2.00% $440,896; assumptions note on screen the whole time Ch5) SPY + 200-day chart (HYPOTHETICAL BACKTEST); 8.39% vs 10.93%; drawdown −55% vs −22%; year heatmap; in- vs out-of-sample Ch6) Broker × AI grid; Robinhood permissions quote; red-cross checklist (caps / allowlist / read-only / paper); TradeLens and LiveTradeBench charts; WARNING EXAMPLE frame Ch7) [PLACEHOLDER: fill from recording] Grok connector + consent + $500 transfer + lockdown + PROMPT D; rule card with SHA-256; LIVE / SHADOW / BENCH legend; REF → CONFIRM chat Ch8) 15%/week counter ('MATH OF THE CLAIM'); CFTC/SEC case cards; 7-tick red-flag checklist Ch9) KEEP / SKIP board; neutral scorecard; recap cards; final LIVE vs SHADOW vs BENCH [placeholder] | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Long-form: every chart is our own motion graphic (no third-party dashboard screenshots). Persistent labels: AS REPORTED (Alpha Arena), HYPOTHETICAL BACKTEST (Ch5), the fee convention line (Ch4). In Ch7, blur everything except the last 4 of the Agentic account. Chapter hold ≤5 s. Ends on 'Drop a comment'. | No CapCut kit yet. Data: research/ai-bots/ (sma200_results.md, fee_drag_30y_results.md, live-experiment-rules-v1.1.md), research/ai-bots-investing-dossier.md, research/ai-agents-x-brokers-matrix.md | Researcher: re-verify research by Thu 10/1 (Robinhood pages, SPIVA mid-year PDF, official Alpha Arena table). Then you lock the post date. Cold open, Ch1–6 and Ch8–9 can be voiced once a voice is picked; Ch7 waits for footage.
6 | Report: Tesla Builds Hundreds of Optimus Robots a Week. So Why Can't They Do Much Yet? (Receipts #1) | PARADOCS10X | Long (10–14 min) | IN BUILD. VO chapters exist but use the RETIRED Marcus voice, so a re-voice decision is needed. No final export. Packaging is a draft (3 titles and 3 thumbnails to pick from). | scripts/tech-01-optimus.proofed.md + scripts/optimus-first60-v2.proofed.md (new cold open) · proofed; Oct 1 lock re-check pending | Rough-cut lock Thu 10/1 5:00 PM · packaging pick Thu 10/1 5:00 PM · CD export Thu 10/1 9:00 PM · POST Fri 10/2 10:00 AM AZ | Cold open) 'HUNDREDS / WEEK' over an official Optimus still + REPORTED tag from frame 0; Electrek/The Information headline card + NOT CONFIRMED BY TESLA stamp; Model S/X press image → Fremont blueprint, 'S/X LINE' struck → OPTIMUS; Q2 Update production-line photo The report) Headline card; block chart 'few dozen → several hundred / wk (~10×)'; Q2 Update PDF highlight; 'OPTIMUS → trains → OPTIMUS' loop Receipts) Timeline of dated quote cards (Jun 2024 → Jan 2025 → Jan 2026); '10,000' shrinks with a 'Probably not.' sticker; card flips to 'Not in usage in a material way'; dashed 1,000,000/YEAR; flat S-curve Where they go) Official Tesla clips (≤5–8 s, labels kept); funnel TESTING · TRAINING · DATA; V3 vs COMMERCIAL silhouettes; Agility Digit totes + Figure at BMW footage; world map (~13,000 humanoids, Omdia); bars with Tesla 'NOT DISCLOSED' Hands) Hand cutaway (ILLUSTRATION); dexterity quote card; REWORK loop; sensing glove; Brooks photo; 17,000-dot hand; match-lighting ANIMATION; '500,000+ HOURS' data-collector callout Brain) Moravec quote card; Narayanan headline card; task grid; REACH/GRASP/PLACE tiles + DAY 1–3; 'no one's ever achieved this' card; humanoid vs arm; official Atlas clip Change my mind) Checklist receipt card, icons tick on Scorecard) 6 rows slam in with callbacks → 22 / 60 Verdict) REAL / OVERHYPED / TOO EARLY stamp → TOO EARLY; two progress bars; Fremont aerial pull-out; keep the end-screen zone clear for the last 20 s | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Long-form: hero image per beat, no hold longer than ~5 s. Every on-screen number carries its source tag (SOURCE / REPORTED / COMPANY CLAIM / ESTIMATE / OPINION). Official or licensed robot footage only, never sped up. No AI video of real robots. Ends on the spoken comment CTA, then the end screen. | No CapCut kit in /workspace/capcut-kits/ yet. VO (retired voice): /workspace/audio/optimus-vo/ · Footage: /workspace/broll/optimus/ (broll-index.md) · Packaging: social/optimus-packaging.md | You: decide the re-voice (new voice vs keep) TODAY and pick title and thumbnail by Thu 5 PM (recommended A + 1). Then CD/Editor rough cut → lock Thu 5 PM → export 9 PM → you post Fri 10 AM with the AI-use setting on.
7 | Grok + Robinhood $500 live experiment (signup/Day-0 recording → 30 sessions) | The Meticulous Investor | Footage for Long (tutorial + flagship Ch7) | Rules v1.1 approved 1:19 PM Tue 9/29. Funding PENDING. Nothing recorded yet. | scripts/money-long-grok-robinhood-tutorial.proofed.md (8–12 min tutorial) · proofed, blocked on footage · plus flagship Ch7 · rules: research/ai-bots/live-experiment-rules-v1.1.md · steps: research/ai-bots/day0-setup-guide.md | Signup/Day-0 recording by Fri 10/2 · trading starts Mon 10/5 (sessions 6:50–7:50 AM AZ per the rules). Tutorial post: tracker proposes Thu Nov 5, conditional | Day-0 recording list (from the tutorial placeholders): 1) Grok chat '+' → Add connector → Custom (or grok.com/connectors → New Connector) 2) Paste https://agent.robinhood.com/mcp/trading into the connector form 3) Robinhood sign-in/consent screen (blur the email) 4) Agentic account opens; cash vs limited-margin choice 5) Transfer review '$500.00 → Agentic' (blur balances, bank, and all account numbers except the Agentic last 4) 6) Lockdown: CASH, options off, crypto agreement NOT accepted, push notifications on, disconnect button 7) New chat → PROMPT D (read-only) → Grok's reply with tool names + any approval prompt 8) Go/no-go G1–G9 ticking From 10/5: full Grok session, review_equity_order, CONFIRM message, fill report, push notification, order detail | Raw screen capture on desktop (Robinhood requires desktop for Agentic signup). Close tabs, notifications off, never record the password or 2FA. Then in CapCut: blur personal data (Mosaic, tracked); ≤3-word captions on each step; punch-in on each button as it's named; SFX on each click. The real UI is the hero shot. | No kit yet. Record to the box or desktop. Log: research/ai-bots/live-experiment/ (trades.csv, signal_check.py) | You: fund $500, record the signup/Day-0 by Fri 10/2, run PROMPT D, confirm go/no-go. Sessions start Mon 10/5.
8 | Alpha Arena: 6 AIs Got Real Money to Trade | PARADOCS10X | Short | FINAL, QA passed 4:09 PM Tue 9/29 after the re-voice plus the DeepSeek 'five percent' line fix (32.84 s). Ready to post. | scripts/tech-short-alpha-arena-6-ais-real-money.proofed.md · proofed. TTS: shorts/revoice/arena.tts.txt | Fri 10/2 or Sat 10/3 | 1) Payoff at frame 0: rebuilt leaderboard, 4 red bars plunging (GPT-5 / GROK 4 / CLAUDE / GEMINI), chip 'OCT–NOV 2025', REPORTED tag 2) Red bars land: Claude −31.09%, Grok −45.45%, Gemini ~−56%, GPT-5 −62.66%* + footnote 3) Title card 'ALPHA ARENA · Season 1 · Oct 18–Nov 3, 2025 · Hyperliquid · $10K each' 4) Green bars rise: Qwen3 Max +22.31%, DeepSeek V3.1 +4.89% (2 OF 6 MADE MONEY) 5) Full 6-row leaderboard, famous names at the bottom → end card DROP A COMMENT / WHO'D YOU BET ON? | LOCKED FINAL, post as is (built and QA'd to this standard: kinetic word-pop captions, SFX, CTA end card held ≥0.6 s). Only open it in CapCut to fix something that QA flagged. Charts are rebuilt (no nof1 screenshots). 'REPORTED' stays on every frame. | Final: /workspace/shorts/tech-2026-09-29-alpha-arena-6-ais.mp4 · Cover: /workspace/style/covers/tech-6-ais-trading.png · Copy: shorts/publish-copy-2026-09-29-extra.md §D | You: upload Fri/Sat with the AI-use setting on and pin the comment. If Fri, don't let it collide with the Optimus long at 10 AM (post it later in the day or on Sat).
9 | How It Actually Works #1: Why Robot Hands Are the Hardest Problem in Humanoids | PARADOCS10X | Long (10–12 min) | NOT STARTED. Research brief exists; no script. | None · not written. Research: research/robot-hands-brief.md + robot-hands-numbers.csv | Script by Tue 10/6 (tracker) · POST Fri 10/9 | TBD – script not written | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Series format: surprising fact → 3 layered chapters, each ending on a question → misconceptions → what's next. Diagrams are the hero shots. | None yet | Researcher → Script Writer: script by 10/6. CD/Editor then build a CapCut kit for you.
10 | Receipts #2: Roadster (after the Oct 15 event) | PARADOCS10X | Long | NOT STARTED. Research prefill exists; the script waits for the Oct 15 event. | None · not written. Research: research/roadster-receipts-prefill.md, tesla-roadster-numbers.csv, tesla-roadster-launch.md | Script right after the Thu 10/15 event · POST Fri 10/16 | TBD – script not written | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Long-form Receipts template (split-screen claim vs receipt, date-card stack). Reuse the Short's 13-date graphics. | None yet. Graphics to reuse: shorts/build_roadster/ | Researcher/Script Writer: draft the night of 10/15. Then swap the Roadster Short's related-video link to this video.
11 | OpenAI Dots vs Grok Bot: One Agent or a Team? | PARADOCS10X | Short (~53 s) | CapCut KIT DELIVERED (VO + footage + graphics + timeline). Blocked on YOUR screen recording (slots 1–3). | scripts/tech-short-dots-vs-grok-bot.proofed.md · proofed. Timeline: capcut-kits/dots-vs-grok-bot/script-timeline.md | No date set in the files. News-timely (DevDay was Tue 9/29), so post as soon as it's finished | 1) Split: OpenAI Dots characters/cloud computer (L) vs Grok Bot shared desktop [REC 1] (R) 2) Punch to full screen: several agent screens on one computer [REC 1]; dot splits into a cluster (g03→g04) 3) VS plate: Todd character vs cluster (cut first if long) 4) DevDay film still → recap card → ALWAYS-ON → GPT-6 ASTRA; characters pop in 5) Dot + browser → cloud computer → 4,000+ APPS counter with logos 6) Pan across agent names, snap to the tiled agent screens [REC 1b] 7) Agents messaging + a scheduled routine firing [REC 3] 8) Split: OpenAI 'review before merge' image vs Grok Bot approval card [REC 2] 9) ChatGPT / Slack / Teams logos slam in, 'TEXTING: SOON' chip 10) PRO · BUSINESS PREMIUM badges → 'PRO: NOT EEA/UK/CH' 11) 'PAID CURSOR OR SUPERGROK' card + logos over REC 1 12) Collapse to one glowing dot + 'FOR NOW' 13) Ghost cluster vs connected cluster over the group chat [REC 3] 14) End card: characters vs cluster, 'ONE AGENT? WHOLE CREW?' + comment icon, hold 0.5–1 s | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Kit-specific: word-pop captions of 1–3 words at the timeline timestamps; push-ins, whip pans, impact + shake/flash with a whoosh/impact/riser SFX on every hit; source footer at y≈1400 only. BLUR all personal data in the recording (Mosaic, tracked), keep only agent names; crop 'Avril Chen' out of image 06. If it's long, cut 'What's different?' first. | /workspace/capcut-kits/dots-vs-grok-bot/ (vo.wav, footage/, graphics/, cover.png, publish-copy.md, qa/) · zips: dots-vs-grok-bot.zip, dots-kit-part1-vo-script-graphics.zip, dots-kit-part2-footage.zip | You: record REC 1 (shared desktop/agent names/tiles), REC 2 (approval card) and REC 3 (agent messages + a routine firing); grab the Cursor and SuperGrok logos (not in the kit); assemble in CapCut; post with the AI-use setting on.
12 | Robinhood's AI Can Trade Without Asking, If You Opt In | The Meticulous Investor | Short | SAVED FOR LATER. Script proofed; VO deferred; visual draft only. | scripts/money-short-robinhood-ai-trades-without-asking.proofed.md · proofed. TTS: shorts/revoice/robinhood.tts.txt | Unscheduled (tracker suggests Wed 10/21 TMI, only as a swap) | 1) Payoff at frame 0: rebuilt fine-print line, 'without your confirmation' highlighted; Grok/ChatGPT/Claude tags orbit an order ticket 2) Zoom into a rebuilt Robinhood support-page graphic (ROBINHOOD'S OWN WORDS) 3) Verbatim quote types out; 'without your confirmation' stamps red 4) Checklist rows flip to 'Not found': Paper mode / Order caps 5) Account cards light up; only one says 'Agentic' (READS ALL · TRADES ONE) 6) 'Ask before trading' toggle, OPT-IN label → end card DROP A COMMENT | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Use the real Robinhood Agentic UI from the Day-0 recording (blurred) in place of the rebuilt mock where possible. | Visual draft: /workspace/shorts/build_robin/ · re-voice config: shorts/revoice/robinhood.json | You: pick a slot. Then re-voice + build (or a CapCut kit). Re-verify the Robinhood pages first.
13 | Fee Short (working title; fee drag over 30 years) | The Meticulous Investor (likely; money topic) | Short | SAVED FOR LATER. No Short script. | None · not written. Parent material: flagship Ch4 (scripts/money-long-ai-trading-flagship.proofed.md) + research/ai-bots/fee_drag_30y_results.md | Unscheduled | TBD – script not written | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. | None yet | Script Writer, when you slot it: cut a 25–30 s script from flagship Ch4.
14 | 200-day-rule Short (working title; SMA200 backtest) | The Meticulous Investor (likely; money topic) | Short | SAVED FOR LATER. No Short script. | None · not written. Parent material: flagship Ch5 + research/ai-bots/sma200_results.md | Unscheduled | TBD – script not written | Standard: 1 hero image/beat · ≤3 words on screen · real footage/UI, no stock · saturated color, dramatic light · cut every 1–1.5 s · kinetic captions + SFX on every hit · end on the spoken CTA. Label every frame HYPOTHETICAL BACKTEST (same as flagship Ch5). | None yet | Script Writer, when you slot it: cut a 25–30 s script from flagship Ch5.